## ROAD MAP ES
Roadmap First Year Activities - Spain
[6 empty] | Workshop Turkey | Meeting in Lithuania |  |  | Meeting in GERMANY | YEAR REPORT | Meeting in Bulgaria
| SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JUNE | JULY
TASKS
MANAGEMENT
Participate in the Kick-off | DECEMBER: Kick off
Understand and produce financial documents | SEPTEMBER: permanent collection of documents according to protocols
Get contract /protocols signed | JANUARY: All contracts
Partners to provide signed Bank payment document | JANUARY: Signed document
Creating the draft roadmap for the project | DECEMBER: Road map deliver
Road map follow up | JANUARY: permanent follow up
Collecting data for the year report | DECEMBER: permanent data collection
Collect own dissemination material | DECEMBER: permanent collection of dissemination materials
Own financial management | SEPTEMBER: permanent collection/sending according to protocols
Internal reports-1-2- | Meeting in Lithuania MARCH: Deliver 1 report; Meeting in GERMANY JUNE: Deliver 2 report
IOS 1
Consolidate one study analysis which addresses current and projected smart services and in-service training services, innovative teaching methodologies at consortium level | JANUARY: Report delivered
First Matrix + Matrix upgrade | JANUARY: Matrix delivered
IOS 2
Give feedback on TURKISH 5 SMART SERVICES | Meeting in Lithuania MARCH: Feedback on LT to iterate; Meeting in Lithuania APRIL: working on TR/LTiterations; Meeting in GERMANY JUNE: Feedback iterations results TR
Give feedback on LITHUANIAN 5 SMART SERVICES | Meeting in Lithuania MARCH: Feedback on TR; Meeting in Lithuania APRIL: working on TR/LTiterations; Meeting in GERMANY JUNE: Feedback iterations results LT
Design + Run workshop W2 | Meeting in Lithuania MARCH: Workshop 2; Meeting in Lithuania APRIL: Matrix upgrade based on findings prototypes and feedback from partners
IOS 3 | YEAR REPORT JUNE: contribute to report
Design + Run Workshop -3 DE | Meeting in Lithuania MARCH: Feedback LT/TR/workshop 2; Meeting in GERMANY JUNE: Feedback LT/TR/DE/workshop 3
Provide feedback on DE/TR/LT SMART Services | bar: Meeting in Lithuania MARCH; Meeting in GERMANY JUNE
IOS4 | YEAR REPORT JUNE: contribute to report
Run Bulgarian workshop including content+participants+ 5 SMART services definition | bar: DECEMBER to YEAR REPORT JUNE
running +reporting four workshop | Meeting in Bulgaria JULY: Workshop deliver
prototyping 5 SMART Services defined | Meeting in Bulgaria JULY: Final version of 5 SMART
iterate services based in local and partner feedback | Meeting in Lithuania MARCH: working on TR/LTiterations; Meeting in Lithuania APRIL: working on TR/L Titerations; Meeting in GERMANY JUNE: working on TR/LT/DE iterations; YEAR REPORT JUNE: working on TR/LT/DE iterations; Meeting in Bulgaria JULY: national/international insights via platform
Workshop report + social media upload | Meeting in Bulgaria JULY: all media uploaded
5 SMART prototypes uploaded to the platform | Meeting in Bulgaria JULY: Platform upload
Matrix upgrade | Workshop Turkey FEBRUARY: Matrix upgrade based on findings prototypes and feedback from partners
Dissemination
Disseminate Project information in English material | DECEMBER: permanent dissemination
Organise other workshops connected to other events | Meeting in Lithuania MARCH: ACCORDING TO SCHEDULE IF POSSIBLE
Create Project Social Media channels Facebook-Twitter-VIMEO-Pinterest-Instagram to post only project activities | JANUARY: Social MEDIA LT; Workshop Turkey FEBRUARY: permanent update
Create Smore flyers in English | Meeting in Lithuania MARCH: SMORE 1; Meeting in Lithuania MAY: SMORE 2; Meeting in GERMANY JUNE: SMORE 3; Meeting in Bulgaria JULY: SMORE 4
Newsletters project achievements in English | DECEMBER: WEBSITE info PUBLISHED; JANUARY: permanent upgrade
[8 empty] | news 1 |  |  | news 2
Note on A44: *: Definir #hastag
Note on A46: *: *: google search facebook pages of libraries in the country to send project information to post.
Note on F44: *: based on xlibrisproject English version material + local material http://facebook.com/xlibris http://twitter.com/xlibrisproject http://pinterest.com/xlibrisproject
Note on H4: *: All meetings are 5 days 1 management 2 in service training - 2 SMART SERVICES with final users
Note on H17: *: READ PROTOCOLS ORIGINALS
Note on H24: *: Partners will give to feedback on the services you may adopt some of the comments to iterate the service. In any case prototyping at local level continues till nex meeting.
Note on I24: *: *: Iterations means the work you do in between meetings to feedback or prototype at local level any of the SMART SERVICES developed by the partners.
Note on K4: *: All meetings are 5 days 1 management 2 in service training - 2 SMART SERVICES with final users
Note on K17: *: *: READ PROTOCOLS ORIGINALS
Note on M4: *: All meetings are 5 days 1 management 2 in service training - 2 SMART SERVICES with final users
Note on M34: *: Of workshop we should come out with the propotype of the new SMART services that could be transformed into OER. Report on the workshop findings is produced as part of the Methodology book.
Note on M35: *: Here you present your results that are going to be transformed into OER and MOOCs
Note on M36: *: after each workshop SMART ICT services are uploaded to platform to get on-line insights within the community