## ROAD MAP LT
Roadmap First Year Activities - Lithuania
[6 empty] | Workshop Turkey | Meeting in Lithuania |  |  | Meeting in GERMANY | YEAR REPORT | Meeting in Bulgaria
| SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JUNE | JULY
TASKS
MANAGEMENT
Participate in the Kick-off | DECEMBER: Kick off
Understand and produce financial documents | SEPTEMBER: permanent collection of documents according to protocols
Get contract /protocols signed | JANUARY: All contracts
Partners to provide signed Bank payment document | JANUARY: Signed document
Creating the draft roadmap for the project | DECEMBER: Road map deliver
Road map follow up | JANUARY: permanent follow up
Collecting data for the year report | DECEMBER: permanent data collection
Collect own dissemination material | DECEMBER: permanent collection of dissemination materials
Own financial management | SEPTEMBER: permanent collection/sending according to protocols
Internal reports-1-2- | Meeting in Lithuania MARCH: Deliver 1 report; Meeting in GERMANY JUNE: Deliver 2 report
IOS 1
Delivering one study analysis which addresses current and projected smart services and in-service training services, innovative teaching methodologies | JANUARY: Report delivered
First Matrix + Matrix upgrade | JANUARY: Matrix delivered
IOS 2 | YEAR REPORT JUNE: contribute to report
Drafting Lithuanian workshop including content+participants + 5 SMART services definition | bar: DECEMBER to Workshop Turkey FEBRUARY
running +reporting first workshop | Meeting in Lithuania MARCH: Workshop deliver
5 SMART Services defined | Meeting in Lithuania MARCH: 5 SMART SERVICES
iterate services based in local and partner feedback | Meeting in Lithuania MARCH: Feedback to iterate; Meeting in Lithuania APRIL: working on TR/LT iterations; Meeting in GERMANY JUNE: Present iterations results; YEAR REPORT JUNE: working on TR/LT iterations; Meeting in Bulgaria JULY: Final version of 5 SMART
Workshop report + media upload | Meeting in Lithuania MARCH: all media uploaded
5 prototypes uploaded to the platform | Meeting in Lithuania MARCH: Platform upload; Meeting in Lithuania APRIL: national/international insights via platform; Meeting in Bulgaria JULY: International insights report
Give feedback on TURKISH 5 SMART SERVICES | Meeting in Lithuania MARCH: Feedback on TR
Matrix upgrade | Workshop Turkey FEBRUARY: Matrix upgrade based on findings prototypes and feedback from partners
IOS3
Participate in Workshop 3 | Meeting in GERMANY JUNE: workshop 3
Present iterations of own LT 5 SMART | Meeting in GERMANY JUNE: present iterations on LT
Provide feedback on SMART DE/TR | Meeting in GERMANY JUNE: iterations DE/TR
IOS 4
Participate in Workshop 4 | Meeting in Bulgaria JULY: workshop 4
Present final version of 5 SMART SERVICES | Meeting in Bulgaria JULY: Final version of 5 SMART
Provide feedback on DE/TR/BG SMART Services | Meeting in Bulgaria JULY: Provide feedback
Dissemination
Disseminate Project informaiton in Lithiuanian material | DECEMBER: permanent dissemination
Organise other workshops connected to other events | Meeting in Lithuania MARCH: ACCORDING TO SCHEDULE IF POSSIBLE
Create Lithuanian Social Media channels Facebook-Twitter-VIMEO-Youtube-Instagram to post only project activities | JANUARY: Social MEDIA LT; Workshop Turkey FEBRUARY: permanent update
Create own Smore flyers in Lithuanian | Meeting in Lithuania MARCH: SMORE 1; Meeting in Lithuania MAY: SMORE 2; Meeting in GERMANY JUNE: SMORE 3; Meeting in Bulgaria JULY: SMORE 4
Website publishing/update/Newsletters to tackle all libraries/schools at national level | DECEMBER: WEBSITE info PUBLISHED; JANUARY: permanent upgrade
[8 empty] | news 1 |  |  | news 2
Note on A46: *: define #hashtag
Note on A48: *: google search of libraries facebook pages to send the project info.
Note on H4: *: All meetings are 5 days 1 management 2 in service training - 2 SMART SERVICES with final users
Note on H17: *: *: READ PROTOCOLS ORIGINALS
Note on H25: *: Of workshop we should come out with the propotype of the new SMART services that could be transformed into OER. Report on the workshop findings is produced as part of the Methodology book.
Note on H27: *: Partners will give to feedback on the services you may adopt some of the comments to iterate the service. In any case prototyping at local level continues till nex meeting.
Note on J27: *: Iterations means the work you do in between meetings to feedback or prototype at local level any of the SMART SERVICES developed by the partners. It also includes yours.
Note on K4: *: All meetings are 5 days 1 management 2 in service training - 2 SMART SERVICES with final users
Note on K17: *: *: READ PROTOCOLS ORIGINALS
Note on M4: *: All meetings are 5 days 1 management 2 in service training - 2 SMART SERVICES with final users
Note on M27: *: Here you present your results that are going to be transformed into OER and MOOCs
Note on M40: *: Here you present your results that are going to be transformed into OER and MOOCs