## ROAD MAP TR
Roadmap First Year Activities -Turkey
[6 empty] | Workshop Turkey | Meeting in Lithuania |  |  | Meeting in GERMANY | YEAR REPORT | Meeting in Bulgaria
| SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JUNE | JULY
TASKS
MANAGEMENT
Organizing the Kick-off | DECEMBER: Kick off
Get partners financial documents | SEPTEMBER: permanent collection of document according to protocols
Get contract signed | JANUARY: All contracts
Paid partners | JANUARY: Payment done
Creating the logo | DECEMBER: Logo delivered
Creating the project website | DECEMBER: website delivered
Preparing the Partnership Protocols | DECEMBER: Protocol done
Creating the draft roadmap for the project | DECEMBER: Road map deliver
Road map follow up | JANUARY: permanent follow up
Collecting data for the year report | DECEMBER: permanent data collection
Collects partners dissemination material | DECEMBER: permanent collection of dissemination materials
Own financial management | SEPTEMBER: permanent collection according to protocols
Year Report | SEPTEMBER: data collecting; YEAR REPORT JUNE: Year report
IOS 1
Delivering one study analysis which addresses current and projected smart services and in-service training services, innovative teaching methodologies | JANUARY: Report delivered
First Matrix + Matrix upgrade | JANUARY: Matrix delivered
IOS 2
Drafting Turkish workshop including content+participants | bar: DECEMBER to JANUARY
running +reporting first workshop | Workshop Turkey FEBRUARY: Workshop deliver
5 SMART Services defined | Meeting in Lithuania MARCH: LT -Presentation
iterate services based in local and partner feedback | Meeting in Lithuania MARCH: Feedback to iterate; Meeting in Lithuania APRIL: working on iterations; Meeting in GERMANY JUNE: Present iterations results; Meeting in Bulgaria JULY: Final version of 5 SMART
Workshop report + media upload | Workshop Turkey FEBRUARY: all media uploaded
5 prototypes uploaded to the platform | Workshop Turkey FEBRUARY: Platform upload; Meeting in Lithuania MARCH: national/international insights via platform; Meeting in Bulgaria JULY: International insights report
Matrix upgrade | Workshop Turkey FEBRUARY: Matrix upgrade based on findings prototypes and feedback from partners
Dissemination
Disseminate English material | DECEMBER: permanent dissemination
Organise other workshops connected to other events | Meeting in Lithuania MARCH: ACCORDING TO SCHEDULE IF POSSIBLE
Create Turkish Social Media channels | JANUARY: Social MEDIA TR; Workshop Turkey FEBRUARY: permanent update
Create own Smore flyers | Meeting in Lithuania MARCH: SMORE 1; Meeting in Lithuania MAY: SMORE 2; Meeting in GERMANY JUNE: SMORE 3; Meeting in Bulgaria JULY: SMORE 4
Website publishing/update/Newsletters | DECEMBER: WEBSITE PUBLISHED; JANUARY: permanent upgrade
[8 empty] | news 1 |  |  | news 2
Note on G29: *: Of workshop we should come out with the propotype of the new SMART services that could be transformed into OER. Report on the workshop findings is produced as part of the Methodology book.
Note on H30: *: You present to your partners the activity , how was organized, done and the results. We reflect in who can capitalize in the model to find replicability between meetings.
Note on H31: *: Partners will give to feedback on the services you may adopt some of the comments to iterate the service. In any case prototyping at local level continues till nex meeting.
Note on M31: *: Here you present your results that are going to be transformed into OER and MOOCs